## Week 1-2
Computer Science 2 Project | Team Members: | Jave Ivan I. Valeza
Group Progress Report |  | Dion Edric A. Bingco
4th Quarter
Week 1 - 2 March 2-13
GOAL / State your goal for the Week | DATA COLLECTED / State/list the data collected relevant to your project | PROGRESS / State the progress you have made so far by the end of the week
Design thinking | Design Idea | Completed the first implementation of the design and the initial web app setup.
Researching how to integrate Python code into HTML | Research materials, frameworks, and documentation for Python web app conversion. | Completed the first implementation of the design and the initial web app setup.
STRENGTH
Clear vision and execution of the initial transition from a basic Python script to a functional web application design.
AREAS FOR DEVELOPMENT
Deepening technical proficiency with the selected Adapting Python code to work smoothly within a web-based user interface.
STRATEGY FOR SUCCESS
Dedicate time to understanding web app frameworks to ensure the design implementation holds up in the next phases..

## Week 3-4
Computer Science 2 Project | Team Members: | Jave Ivan I. Valeza
Group Progress Report |  | Dion Edric A. Bingco
4th Quarter
Week 3 - 4 March 16-27
GOAL / State your goal for the Week | DATA COLLECTED / State/list the data collected relevant to your project | PROGRESS / State the progress you have made so far by the end of the week
Finalize the design for the web app | UI/UX layouts for application navigation | Successfully added all planned buttons (Home, To-Do, Calendar, Dark/Light Mode, Exit)
Determine necessary navigation buttons (Home, To-Do, Calendar, Dark/Light mode). | conceptualizating security features. | Started planning a security feature.
STRENGTH
Rapid prototyping and successful integration of core user interface components and navigation buttons.
AREAS FOR DEVELOPMENT
Ensuring all added buttons route correctly without breaking the web app's layout.
STRATEGY FOR SUCCESS
Conduct thorough click-testing on the newly added buttons (Home, To-Do, Calendar, Dark/Light Mode) before moving on to executable conversion.

## Week 5-6
Computer Science 2 Project | Team Members: | Jave Ivan I. Valeza
Group Progress Report |  | Dion Edric A. Bingco
4th Quarter
Week 5 - 6 March 30, 31,
GOAL / State your goal for the Week | DATA COLLECTED / State/list the data collected relevant to your project | PROGRESS / State the progress you have made so far by the end of the week
Address teacher feedback to declutter user navigation | User feedback from the teacher regarding UI clutter | Compiled a usable .exe web app featuring a proper home, switchable to-do list, and dark/light mode.
Fix the calendar issue where top-level inputs are hidden. | Calendar bug | Navigation was simplified and the calendar bug was successfully fixed by making popup display inside.
STRENGTH
Excellent receptiveness to feedback and quick turnaround on bug fixes, built it into a .exe file.
AREAS FOR DEVELOPMENT
Fixing the remaining minor issues in user navigation ensuring the user will only do a minimal amount of navigation.
STRATEGY FOR SUCCESS
Perform iterative user testing specifically on the calendar UI to guarantee all inputted days and tasks are clearly visible.

## Week 7
Computer Science 2 Project | Team Members: | Jave Ivan I. Valeza
Group Progress Report |  | Dion Edric A. Bingco
4th Quarter
Week 7 April 6-7
GOAL / State your goal for the Week | DATA COLLECTED / State/list the data collected relevant to your project | PROGRESS / State the progress you have made so far by the end of the week
Finalize the 'Timely' app features | Telegram Bot API documentation and chat ID retrieval methods for the notification system. | Final app delivered.
Integrating the Telegram bot for notifications, advanced To-Do list interactions, and polishing the UI. | Finalized our app features | Features include account switching, Telegram notifications, draggable/updatable To-Do list, dynamic calendar with time-based alerts, and animated exit sequences.
Add better navigation features | Calendar issues to be fixed | Added calendar date navigator, where user can pick a year and month instead of scrolling through the whole calendar.
STRENGTH
Successfully integrated complex third-party APIs (Telegram) and implemented highly advanced UI interactions (drag-and-drop tasks, warning prompts, animations, using CSS and HTML).
AREAS FOR DEVELOPMENT
Maintaining code cleanliness and scalability given the heavy addition of complex features.
STRATEGY FOR SUCCESS
Perform a final code cleanup, verify the Telegram API error handling (in case of lack of internet), and finalize the project documentation.