## week1
Computer Science 2 Project | Team Members: | Jave Ivan I. Valeza
Group Progress Report |  | Dion Edric A. Bingco
3rd Quarter
Week 1 - Jan 16, 2026 (covers week 1-3 of proj sched)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Preparations for coding | Order of coding. | Done
Find suitable codes to borrow on
Github | None | Found none to borrow
STRENGTH
Clear planning in what we are gonna do
Plan to make project from scratch
AREAS FOR DEVELOPMENT
Coding
Learning how to code
STRATEGY FOR SUCCESS
Borrow code from github and cite the coder.

## week2
Computer Science 2 Project | Team Members: | Jave Ivan I. Valeza
Group Progress Report |  | Dion Edric A. Bingco
3rd Quarter
Week 2 - Jan 23, 2026 (covers Week 4)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Finish the dark and light mode and | how to change the background color | finished
potentially add a timer. | none | couldn't add
STRENGTH
finished it quickly
AREAS FOR DEVELOPMENT
need to incorporate it to an app
STRATEGY FOR SUCCESS
Continue researching about the topic.

## week3
Computer Science 2 Project | Team Members: | Jave Ivan I. Valeza
Group Progress Report |  | Dion Edric A. Bingco
3rd Quarter
Week 3 - Jan 30, 2026 (covers week 5)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Make app background |  | Done
Research how to make notfication | use plyer plugin for notif system | None
system
STRENGTH
Made app background
AREAS FOR DEVELOPMENT
Notification system
STRATEGY FOR SUCCESS
Research more and download required plugins for the project

## week4
Computer Science 2 Project | Team Members: | Dion Edric Anes Bingco
Group Progress Report |  | Jave Ivan I. Valeza
3rd Quarter
Week 4 - Feb 6, 2026 (covers week 6)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Make calendar |  | Done
Make to-do list |  | Done
Finish notif system |  | None
STRENGTH
Finished quickly and can move on to other sectors of the project
AREAS FOR DEVELOPMENT
Finish notification system
STRATEGY FOR SUCCESS
Work fast with high quality